## Sheet1
Fields | Project Id | New PLM Id | Old Projrct | Old PLM | Actual | Expected | Pass/Fail | Pass/fail
Demand Work Type | 1257536 | 1257538 |  |  | Field is showing mandatory but without Digital/Non-Digital buttons | Showing Digital/Non-digital | Fail
Demand Work Type | 1257536 | 1257542 |  |  | Field is working properly | Showing Digital/Non-Digital | Pass
Demand Work Type | 1257577 | 1257580(VD) |  |  | Field should not editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead | Field is editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead | Fail
Demand Work Type | 1257577 | 1257579(VD) |  |  | Field value should copied from PLM to Position | Field value is copied from PLM to Position | Pass
Demand Work Type | 1257577 | 1257579 |  |  | PLM goes to redefine demand the Demand Work Type should not editable. | Field not editable | Pass
Demand Work Type | 1256245 | 1256340 |  |  | Field should be Non-Digital | Field is Non-Digital | Pass
Position Description And Requirements(Breq 1.11) | 1257537 | 1257539,1257548-AF |  |  | Field is workin Properly | Mandatory when Demand Work Type->Digital | Pass
Position Description And Requirements(Breq 1.11) | 1257537 | 1257552->AF |  |  | Field is showing mandatory | Mandatory when Demand Work Type->Non-Digital | Fail
Position Description And Requirements(Breq 1.11) |  |  | 1256245 | 1256340(Af) | Field should optional in iwfm old project | Field is optional in iwfm old project | Pass
Opportunity ID |  |  | 1254380(VD) |  | Field is showing NA and should be editable | Field is showing NA and editable | Pass
Opportunity ID | 1257577 |  |  |  | Field is showing mandatory and should be editable | Field is shown mandatory and editable | Pass
Digital Transformation Center field | 1257577 | 1257583(VD) |  |  | Field should be editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead. | Field is editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead. | Pass
Digital Transformation Center field | 1257577 | 1257583(VD) |  |  | Field should editable and required when Demand Work type is Digital | Field is editable and required when Demand Work type is Digital | Pass
Digital Transformation Center field | 1257577 | 1257588(VD) |  |  | Field should hidden when Demand Work type is Non- Digital | Field is hidden | Pass
Digital Transformation Center field | 1257577 | 1257583(VD) |  |  | field should not editable on Position detail of the Staffing Profile | field is not editable on Position detail of the Staffing Profile | Pass
Digital Transformation Center field |  |  | 1256245 | 1256340(Af) | field should be hidden | fiels is hidden | Pass
Digital Role Name | 1257537 | 1257578(Af) |  |  | Field should mandatory and editable when Demand work type is Digital | Field is mandatory and editable when Demand work type is Digital | Pass
Digital Role Name | 1257537 | 1257581(Af) |  |  | Field should be hidden | Field is hidden | Pass
Digital Role Name | 1257537 | 1257581(Af) |  |  | Fiels should not be editable in position detail of Staffing Profile | Fiels is not editable in position detail of Staffing Profile | Pass
Digital Role Name | 1257537 | 1257578(Af) |  |  | When user redefine PLM it should go for Auto -Approval | PLM go for Auto-Approval when Redefine | Pass
Digital Role Name |  |  | 1256245 | 1256340 | field should be hidden | fiels is hidden | Pass
Position WBS Id | 1257576 | 1257582(Internal) |  |  | Field should be mandatory and editable when Demand Work Type is Digital and DTC Yes | Field is mandatory and editable when Demand Work Type is Digital and DTC Yes | Pass
Position WBS Id | 1257576 | 1257590(Internal) |  |  | Field should be hidden when Demand work Type is Non-Digital | Fiels is hidden | Pass
Position WBS Id |  |  | 1256245 | 1256340 | Field should be hidden | Field is hidden | Pass
Position WBS Id | 1257576 | 1257615 |  |  | Field should be hidden when Demand Work Type is Digital and DTC No | Field is hidden when Demand Work Type is Digital and DTC No | Pass

## Scenarios
Fields | Project ID | PLM ID | TestSteps | Expected Result | Actual Result | Date of finding | Date of fixing | Defect severiity | Pass/Failed
Demand Work Type | 1257536 | 1257538 | 1)Create a PLM for project 2)user tries to select Demand Work Type field in Position Details | The field should be mandatory and editable by the user | The field was showning mandatory but the field was non editable | 2019-07-02 | 2019-07-02 | blocker | pass
Demand Work Type | 1257577 | 1257580(VD) | 1)User creats an project and PLM 2)PLM send for AE and Org Lead approvals as per requiste | Field is editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead | Field is showing non-editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead | 2019-07-02 |  | blocker | fail
Demand Work Type | 1257577 | 1257579(VD) | 1)User creats a project annd its related PLM 2)user moves till Position cretion 3)verify the position details with PLM | The field values which is created in Position should be same as when we created the PLM | The field values which is created in Position is same as when we created the PLM | 2019-07-02 |  |  | pass
Demand Work Type | 1257577 | 1257579 | 1)user creates aproject and its PLM 2)The user after creating a PLM redefines the demand for the same | PLM goes to redefine demand the Demand Work Type should not editable. | In the redefine demand the field is non editable | 2019-07-02 |  |  | pass
Demand Work Type for existin projects | 1256245 | 1256340 | 1)user in an existing project 2)checks the demand work type field | The Demand wrok type Field should be Non-Digital by default | The Demand wrok type Field is Non-Digital by default | 2019-07-02 |  |  | pass
Demand Work Type | 12567

## Issues
Fields | Project ID | PLM ID | TestSteps | Expected Result | Actual Result | Date of finding | Date of fixing | Defect severiity | Pass/Failed
Demand Work Type | 1257577 | 1257580(VD) | 1)User creats an project and PLM 2)PLM send for AE and Org Lead approvals as per requiste | Field is editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead | Field is showing non-editable by the PM until the PLM is sent for Approval by either the AE or the Org Lead | 2019-07-02 |  | blocker | fail
Position Description And Requirements(Breq 1.11) | 1257537 | 1257552->AF | 1)User creates an project and PLM 2)in PLM page try to create the non digital demand work type and check the postion field | Field should be non mandatory for non Digital field | Field is shown as mandatory for non Digital field | 2019-08-02 |  |  | fail
Position Description And Requirements(Breq 1.11) | 1257537 | 1257552->AF | 1)User creates an project and PLM 2)in PLM page try to create the non digital demand work flow and then check th help docs for it | help doc should be populated for every field | help doc is not showing for many fields | 2019-08-04 |  |  | fail